## Overview
Free template by Darwish Qannan · darwishqannan.com
Growth Team
Weekly overview · Saturday 24 October 2026
PROGRESS BY EFFORT | RUNNING LATE | DUE SOON | DONE THIS WEEK | OPEN TASKS
21.74% | 2 | 3 | 4 | 10
By task count: 38% | 1 blocked | In the next 5 working days | 6 points of work | 36 points still open
Heads up: 38% of the tasks are done, but only 22% of the work. The bigger tasks are still open.
Progress by effort |  |  | Open work by person (points)
[5 empty] | Done | 10
[5 empty] | Remaining | 36
21.74%
0.375
Focus now
Late and blocked work first, then what is due soon.
Task |  | Owner | Due | Status
Prepare board update deck |  | Sara | 2026-10-21 | Late
Competitor review: top 5 players |  | Lina | 2026-10-22 | Late
Fix onboarding email sequence |  | Omar | 2026-10-26 | Blocked
Intern hiring: first interviews |  | Sara | 2026-10-26 | Due soon
Customer survey: send and collect |  | Lina | 2026-10-27 | Due soon
Everything on this page updates from the Tasks sheet. To send it as a picture, use the snapshot on the Weekly Email sheet.
Formulas:
DONE THIS WEEK = IFERROR(INDEX(SORTBY(_xlws.FILTER(Tasks[Due],(Tasks[Status]="Late")+(Tasks[Status]="Blocked")+(Tasks[Status]="Due soon")),_xlws.FILTER(Tasks[SortKey],(Tasks[Status]="Late")+(Tasks[Status]="Blocked")+(Tasks[Status]="Due soon"))),1),"")
22%

## Tasks
Tasks
Type in the white columns. Put a date in Completed when a task is done. The grey columns fill themselves.
ID | Task | Owner | Priority | Effort | Start | Due | Completed | Blocked | Notes | Status | Days | Points | SortKey | LineDone | LineLate | LineBlocked | LineSoon
T-001 | Finalize Q4 campaign brief | Reem | High | M | 2026-10-07 | 2026-10-18 | 2026-10-15 |  |  | Done | Done 15 Oct | 3 | 946313
T-002 | Update pricing page copy | Omar | Medium | S | 2026-10-12 | 2026-10-19 | 2026-10-19 |  |  | Done | Done 19 Oct | 1 | 946314 | - Update pricing page copy (Omar)
T-003 | Prepare board update deck | Sara | High | L | 2026-10-11 | 2026-10-21 |  |  | Waiting for final numbers from finance | Late | 1 working day late | 5 | 146316 |  | - Prepare board update deck (Sara), 1 working day late. Waiting for final numbers from finance
T-004 | Customer survey: send and collect | Lina | Medium | M | 2026-10-15 | 2026-10-27 |  |  |  | Due soon | 3 working days left | 3 | 346322 |  |  |  | - Customer survey: send and collect (Lina), due Tue 27 Oct
T-005 | Fix onboarding email sequence | Omar | High | M | 2026-10-14 | 2026-10-26 |  | Yes | Needs CRM admin access from IT | Blocked | 2 working days left | 3 | 246321 |  |  | - Fix onboarding email sequence (Omar): Needs CRM admin access from IT
T-006 | Shortlist freelance designers | Faisal | Low | S | 2026-10-18 | 2026-10-22 | 2026-10-22 |  |  | Done | Done 22 Oct | 1 | 946317 | - Shortlist freelance designers (Faisal)
T-007 | Competitor review: top 5 players | Lina | Medium | M | 2026-10-13 | 2026-10-22 |  |  | Two profiles left | Late | Was due Thu 22 Oct | 3 | 146317 |  | - Competitor review: top 5 players (Lina), was due Thu 22 Oct. Two profiles left
T-008 | Website speed audit | Faisal | Medium | L | 2026-10-20 | 2026-11-03 |  |  |  | On track | 8 working days left | 5 | 946329
T-009 | Partner webinar logistics | Reem | Medium | M | 2026-10-19 | 2026-10-28 |  |  |  | Due soon | 4 working days left | 3 | 346323 |  |  |  | - Partner webinar logistics (Reem), due Wed 28 Oct
T-010 | Sales one-pager refresh | Sara | Low | S | 2026-10-15 | 2026-10-21 | 2026-10-20 |  |  | Done | Done 20 Oct | 1 | 946316 | - Sales one-pager refresh (Sara)
T-011 | Plan Founding Day promotion | Reem | Medium | M | 2026-11-01 | 2026-11-19 |  |  |  | Not started | 20 working days left | 3 | 946345
T-012 | Clean up CRM duplicates | Omar | Low | M | 2026-10-21 | 2026-11-09 |  |  |  | On track | 12 working days left | 3 | 946335
T-013 | Monthly KPI report | Lina | High | M | 2026-10-18 | 2026-10-24 | 2026-10-24 |  |  | Done | Done 24 Oct | 3 | 946319 | - Monthly KPI report (Lina)
T-014 | Brand guidelines update | Faisal | Low | L | 2026-10-25 | 2026-11-12 |  |  |  | Not started | 15 working days left | 5 | 946338
T-015 | Intern hiring: first interviews | Sara | Medium | M | 2026-10-20 | 2026-10-26 |  |  |  | Due soon | 2 working days left | 3 | 346321 |  |  |  | - Intern hiring: first interviews (Sara), due Mon 26 Oct
T-016 | November social calendar | Reem | Medium | S | 2026-10-05 | 2026-10-12 | 2026-10-12 |  |  | Done | Done 12 Oct | 1 | 946307

## Team
Team load
All open work per person, including tasks that start later, in effort points (S, M, L). Everything here comes from the Tasks sheet.
Faisal is over capacity. Omar, Lina and Reem have the most room for new work.
Person | Open tasks | Open points | Late | Blocked | Due soon | Done this week | Load | Status | Next due | Late pts | Blocked pts | Due soon pts | Other open pts
Sara | 2 | 8 | 1 | 0 | 1 | 1 | 88.89% | Busy | Prepare board update deck · Wed 21 Oct | 5 | 0 | 3 | 0
Omar | 2 | 6 | 0 | 1 | 0 | 1 | 66.67% | OK | Fix onboarding email sequence · Mon 26 Oct | 0 | 3 | 0 | 3
Lina | 2 | 6 | 1 | 0 | 1 | 1 | 66.67% | OK | Competitor review: top 5 players · Thu 22 Oct | 3 | 0 | 3 | 0
Faisal | 2 | 10 | 0 | 0 | 0 | 1 | 111.1% | Overloaded | Website speed audit · Tue 3 Nov | 0 | 0 | 0 | 10
Reem | 2 | 6 | 0 | 0 | 1 | 0 | 66.67% | OK | Partner webinar logistics · Wed 28 Oct | 0 | 0 | 3 | 3
Load = open points ÷ capacity (9 points per person, set in Settings). Above 100% is Overloaded, from 75% is Busy.
Open points by person and status

## Weekly Email
Weekly email
Your report, ready to send: the subject, the text, and a live picture of the Overview.
Subject | Growth Team ¦ Weekly update, 24 Oct 2026
| Text: click the first line below, press Ctrl+Shift+↓ (Mac: Cmd+Shift+↓), then Ctrl+C, and paste. | Snapshot: click the picture, press Ctrl+C, and paste it under the text.
Message | Hi everyone,
Here’s where things stand for Growth Team as of Saturday 24 October.
Progress: 22% of the planned work is complete (6 of 16 tasks).
Completed this week:
- Update pricing page copy (Omar)
- Sales one-pager refresh (Sara)
- Shortlist freelance designers (Faisal)
- Monthly KPI report (Lina)
Running late:
- Prepare board update deck (Sara), 1 working day late. Waiting for final numbers from finance
- Competitor review: top 5 players (Lina), was due Thu 22 Oct. Two profiles left
Blocked:
- Fix onboarding email sequence (Omar): Needs CRM admin access from IT
Coming up in the next 5 working days:
- Intern hiring: first interviews (Sara), due Mon 26 Oct
- Customer survey: send and collect (Lina), due Tue 27 Oct
- Partner webinar logistics (Reem), due Wed 28 Oct
Let me know if anything here looks off.
Thanks,
Sara

## Settings
Settings
Set these once. Every sheet reads from here.
Team name | Growth Team | Effort | Points |  | WeekendCode | 7
Your name | Sara | S | 1
Report date | 2026-10-24 | M | 3 | Keep =TODAY() to report on today, or type a date to freeze a week. "This week" = the 7 days up to it.
Weekend | Friday-Saturday | L | 5 | Used for every working-day count.
"Due soon" window (working days) | 5 | No effort chosen counts as M.
Capacity per person (points) | 9 |  |  | Above this many open points, a person shows as Overloaded. All open tasks count, even future ones.
Team members |  | Public holidays | Name
Sara |  | 2026-09-23 | Saudi National Day
Omar |  | 2027-02-22 | Founding Day
Lina
Faisal
Reem
Add Eid and company holidays in the empty rows.
How it works
1. Add your team members above, and your holidays.
2. On Tasks, replace the sample rows with your own. New rows pick up the formulas by themselves.
3. When a task is finished, put the date in Completed (Ctrl+; types today). That is all the file needs.
4. Status, days left, the Overview and the team load update on their own.
5. At the end of the week, open Weekly Email, copy the text and the snapshot, and send them.
Needs Microsoft 365 or Excel 2021. No macros.
Template by Darwish Qannan · darwishqannan.com · Want it set up for your team? darwishqannan.com/work-with-me